## Sheet1
Task | id | base | part | design | firebase | netlify | react | type | status | completed% | Time(minutes) | date
| KID:001 | / | (header) | page view | null | null | code | code | completed | 100% | 60 | 2021-05-20
| KID:002 | / | (slides) | page view | null | null | code | code | completed | 100% | 60 | 2021-05-21
| KID:003 | / | (rules) | all | null | null | code | code | completed | 100% | 60 | 2021-05-22
| KID:004 | / | (redirect) | all | null | null | code | code | completed | 100% | 100 | 2021-05-23
| KID:005 | / |  | all | null | team | null | deploy | completed | 100% | 60 | 2021-05-24
| KID:006 | /watch | (video) | page view | null | null | code | design | completed | 100% |  | 2021-05-25
| KID:007 | /watch | (fetch) | code | realtime db | null | code | code | completed | 100% |  | 2021-05-26
| KID:008 | /watch | (list) | all | null | null | code | design | completed | 100% |  | 2021-05-27
| KID:009 | /watch | (connect) | code | null | null | code | code | completed | 100% |  | 2021-05-28
| KID:010 | /watch |  | null | null | team | null | deploy | completed | 100% | 60 | 2021-05-29
| KID:011 | /Ranks | (tabel) | page view | null | null | code | design | completed | 100% |  | 2021-05-30
| KID:012 | /Ranks | (fetch) | code | realtime db | null | code | code | completed | 100% |  | 2021-05-31
| KID:013 | /Ranks | (redirect) | code | null | null | code | code | completed | 100% |  | 2021-06-01
| KID:014 | /Ranks |  |  | null | team | null | deploy | completed | 100% | 120 | 2021-06-02
| KID:015 | /suggestion | all | all | realtime db | team | code | deploy | completed | 100% | 150 | 2021-06-03
| KID:016 | /events | all | all | realtime db | team | code | deploy | completed | 100% | 130 | 2021-06-04
| KID:017 | /signup | (card) | all | null | null | code | design | in progress | 40% | 80 | 2021-06-05
| KID:018 | /signup | (login) | all | realtime db | null | code | code | in progress | 40% | 30 | 2021-06-06
| KID:019 | /signup | (redirect) | all | null | null | code | code | in progress | 40% | 30 | 2021-06-07
| KID:020 | /signup |  | all | null | team | code | deploy | in progress | 40% | 30 | 2021-06-08
| KID:021 | / | [6 empty] | not started | 0% |  | 2021-06-09
| KID:022 | / | [6 empty] | not started | 0% |  | 2021-06-10
| KID:023 | / | [6 empty] | not started | 0% |  | 2021-06-11
| KID:024 | / | [6 empty] | not started | 0% |  | 2021-06-12
| KID:025 | / | [6 empty] | not started | 0% |  | 2021-06-13
| KID:026 | / | [6 empty] | not started | 0% |  | 2021-06-14
| KID:027 | / | [6 empty] | not started | 0% |  | 2021-06-15
| KID:028 | / | [6 empty] | not started | 0% |  | 2021-06-16
| KID:029 | / | [6 empty] | not started | 0% |  | 2021-06-17
| KID:030 | / | [6 empty] | not started | 0% |  | 2021-06-18
| KID:031 | / | [6 empty] | not started | 0% |  | 2021-06-19
| KID:032 | / | [6 empty] | not started | 0% |  | 2021-06-20
| KID:033 | / | [6 empty] | not started | 0% |  | 2021-06-21
| KID:034 | / | [6 empty] | not started | 0% |  | 2021-06-22
| KID:035 | / | [6 empty] | not started | 0% |  | 2021-06-23
| KID:036 | / | [6 empty] | not started | 0% |  | 2021-06-24
| KID:037 | / | [6 empty] | not started | 0% |  | 2021-06-25
| KID:038 | / | [6 empty] | not started | 0% |  | 2021-06-26
| KID:039 | / | [6 empty] | not started | 0% |  | 2021-06-27
| KID:040 | / | [6 empty] | not started | 0% |  | 2021-06-28
| KID:041 | / | [6 empty] | not started | 0% |  | 2021-06-29
| KID:042 | / | [6 empty] | not started | 0% |  | 2021-06-30
| KID:043 | / | [6 empty] | not started | 0% |  | 2021-07-01
| KID:044 | / | [6 empty] | not started | 0% |  | 2021-07-02
| KID:045 | / | [6 empty] | not started | 0% |  | 2021-07-03
| KID:046 | / | [6 empty] | not started | 0% |  | 2021-07-04
| KID:047 | [7 empty] | completed | 100% | 110 | 2021-07-05
avg | KID:048 | [7 empty] | in progress | 39.57% | 18 | 2021-07-06
Links
git repo | link
firebase console | link
netlify team | link
product | link

## Sheet2
completed | design
in progress | code
not started | testing
debuggin
deploy